## Summary
Meeting Date | Time | Location / Platform | Attendees | Duration | Next Meeting Date
2025-11-05 | 14:30 | Google Meet | Faisal Shahzad(RP) Tayyab Shahzad(GL) | 19 minutes | 2025-11-12

## Decisions & Discussion
Meeting No | Topic Discussed | Decision Made
1 | Project Idea Discussion — Asked user to explain his idea in detail and share what kind of system he wants to build. Collected all initial requirements through questions. | Finalized the project idea, selected the tools and technologies, and estimated the time required for project development.

## Action Items (Tasks)
Week | Task ID | Assigned To | Description | Deadline | Status | Total task of week | Completed | Pending
First_week | SETUP_REPO | Tayyab Shahzad | Create GitHub repository and set up full project folder structure (Documents, Meeting Minutes, Meeting Videos, Project Files) | 2025-11-06 | Completed
| MEET_RP | Tayyab Shahzad | Conduct first meeting with Requirement Provider (client) | 2025-11-06 | Completed
| GOOGLE_SHEET | Tayyab Shahzad | Create and fill Google Sheet for meeting records (Summary , Attendance, Decisions, Action Items) | 2025-11-07 | Completed
| RP_AGREEMENT | Tayyab Shahzad | Prepare Requirement Provider Agreement (formal collaboration document) | 2025-11-07 | Completed
| TITLE_PAGE | Tayyab Shahzad | Create Title Page (Project title, Subject, Members, Submission date, Department, University) | 2025-11-08 | In Progress
| TOC | Tayyab Shahzad | Write Table of Contents for proposal | 2025-11-08 | In Progress
| INTRO | Tayyab Shahzad | Write Introduction section (project background and importance) | 2025-11-08 | In Progress
| PROBLEM_STMT | Tayyab Shahzad | Write Problem Statement (define key issue and affected users) | 2025-11-09 | In Progress